Jippa

Borrow. Save. Spend globally. Mobile banking that makes life easy.

| # The Problem Zimbabwe is a dollarized, digital economy — 96% of formal transactions are digital (World Bank, 2021) and 7.1M mobile wallets are active (RBZ). But banking products are still built for the formal minority. Whether you’re banked or unbanked, borrowing, saving, and spending globally is harder than it should be. - Borrowing is broken — banks need payslips and collateral. KaShagi caps you at $50. 76% of the economy has no path to credit (ZIMSTAT, 2025). - Saving is painful — USD accounts exist but require branch visits, minimums, and paperwork. No mobile-first option. - Spending globally is gatekept — <16,000 credit cards for 16M people (RBZ). Virtual cards exist but are tied to bank accounts. | # The Solution Jippa is the bank Zimbabwe should already have. Download the app, verify your ID, and get instant access to credit, USD savings, and a virtual card that works anywhere. Banking that works. From your phone. In minutes. The founder already built the scoring engine in Ghana. This is adaptation, not R&D. 1. Borrow: AI credit scoring on your real financial life. Instant $10–$500 loans. Apply in 2 minutes, not 2 weeks. 2. Save: USD savings from your phone. Goals, group savings, auto-deposits. No branch, no minimums. Save more, borrow more. 3. Spend Globally: Virtual Visa/Mastercard in the app. SaaS, imports, e-commerce — anywhere, from your phone. |
| --- | --- |

# Market & Competitive Position

|  | AI Scoring | Savings | USD Cards | Full Stack | Users |
| --- | --- | --- | --- | --- | --- |
| Jippa | ✅ | ✅ | ✅ | ✅ | Pilot |
| EcoCash | ❌ | ❌ | ⚠️ | ❌ | 8.35M |
| InnBucks | ❌ | ⚠️ | ❌ | ❌ | 3M |
| ZB Smile | ❌ | ❌ | ✅ | ❌ | New |

| # Pilot Plan (6–8 Months) Partner with a local licence holder. Validate before scaling. Months 1–2: Secure licence partner, build MVP, adapt scoring model Months 3–4: Closed beta, 200–500 users in Harare, $10–$50 loans Months 5–6: Open beta, 1,000–3,000 users, add USSD channel Months 7–8: 5,000+ users, biz loans, raise seed round with data | # Capital & Unit Economics Raising: $100K–$250K $30–50K Product build + engineering $20–30K Operations, legal, compliance $50–170K Loan book (recycling 2–3x during pilot) Target per-loan economics: Avg loan $50–$150 ¦ Interest 7–12% ¦ Default <5% ¦ Net margin 3–8% Post-pilot seed: $1M–$2M for own licence, savings + cards, national scale |
| --- | --- |

# Founder & Structure

Mo — CEO, Base Technologies BV (Netherlands). Built an alternative credit scoring & microlending platform in Ghana. Built a digital savings app in Ghana. GTM expansion at Paystack (acquired by Stripe for $200M+). BaaS distribution at Anchor.

Corporate structure: Base Technologies BV (Netherlands) → Jippa Technologies (Pvt) Ltd (Zimbabwe, COBE Act subsidiary). At least one Zimbabwe-resident director required (Country Lead). MFI licence partnership sits under the Pvt Ltd.

Why now: This model already works at scale — Nubank reached 120M customers and $8B revenue doing the same thing in Brazil. In Dec 2024 they invested $250M in Africa’s TymeBank. The model is coming to the continent. Jippa gets there first in Zimbabwe.