Jippa

6–8 Month Pilot Roadmap

Mobile banking that makes life easy

Partnership Model |  $100K–$250K Pilot Capital  |  Own App, Own Scoring

A Base Technologies BV venture |  jippa.app  |  CONFIDENTIAL  |  March 2026

# Executive Summary

Jippa is mobile banking that makes life easy. No branches, no paperwork, no payslips. Instant loans powered by AI credit scoring, USD savings, and virtual cards that work anywhere in the world.

Go-to-market strategy: Partner with an existing Zimbabwean licence holder for a 6–8 month pilot with $100K–$250K in capital. Validate the credit scoring model, prove unit economics, and build a user base before raising a seed round to acquire an own licence and scale nationally.

Corporate structure: Jippa is a product of Base Technologies BV, incorporated in the Netherlands. The Zimbabwe operation will run through Jippa Technologies (Pvt) Ltd, a wholly-owned subsidiary registered under the COBE Act. At least one Zimbabwe-resident director is required under Section 195 of COBE. The MFI licence partnership sits under the Pvt Ltd entity.

Market validation: This model already works at scale. Nubank built the same product stack (lending + savings + cards for the underbanked) and reached 120M customers and $8B revenue in Brazil. In Dec 2024, Nubank invested $250M in TymeBank, Africa’s fastest-growing digital bank, confirming the model translates to the continent. Jippa gets there first in Zimbabwe, with a founder who’s already built every product layer in Ghana.

# 1. Licence Partnership Model

Rather than spending 3–12 months and $5M+ acquiring a deposit-taking MFI licence, Jippa will partner with an existing licence holder for the pilot phase. This is how both InnBucks (via Ndoro MicroBank) and Mukuru entered the Zimbabwe market.

## Partner Profile

The ideal partner is a small-to-mid deposit-taking MFI that is RBZ-compliant but lacks technology capability. Jippa brings the app, credit scoring engine, and product design; the partner provides the regulatory umbrella and (optionally) balance sheet capital.

- Candidate types: Kleinfin, Microhub Financial Services, Lion Microfinance, Success Microfinance Bank, or similar RBZ-registered deposit-taking MFIs.

- Deal structure: Revenue share (60–70% Jippa / 30–40% partner) on net interest margin, or pure tech licensing with Jippa funding its own loan book.

- Key term: Option to acquire the partner or obtain own licence at end of pilot, based on performance data.

## Regulatory Requirements (Under Partner’s Licence)

- KYC/AML compliance managed through partner’s existing RBZ framework.

- Data Protection Officer appointment required (new Zimbabwe framework — only 831 orgs compliant by late 2025).

- COBE re-registration by April 2026 — register Jippa as a new entity directly under COBE.

- 7-year retention of KYC documentation and digital onboarding logs per FIU requirements.

- 2% transaction tax on mobile money and 15% digital services tax factored into unit economics.

# 2. Pilot Timeline (6–8 Months)

## Phase 1: Build (Months 1–2)

Goal: Licence partnership signed. MVP app built. Credit scoring model adapted to Zimbabwe data sources.

### Licensing & Legal

- Identify and approach 3–5 potential licence partners. Run due diligence on their RBZ compliance status, balance sheet, and willingness to partner.

- Sign partnership agreement with revenue share terms and post-pilot acquisition option.

- Register Jippa Technologies (Pvt) Ltd under COBE Act as a wholly-owned subsidiary of Base Technologies BV. Appoint Zimbabwe-resident director (Country Lead) and local company secretary. Appoint DPO. Engage local compliance counsel.

### Product & Tech

- Build mobile app (Flutter for cross-platform) with core flows: onboarding, KYC, scoring, loan application, disbursement, repayment.

- Adapt Ghana credit scoring model to Zimbabwe data sources: EcoCash/InnBucks transaction history, ZESA utility payments, airtime purchase patterns, phone metadata.

- Integrate mobile money disbursement and repayment rails (EcoCash at minimum, ideally also InnBucks and bank transfer).

- Build USSD fallback channel for feature phone users.

### Team (3 Key Hires)

- Zimbabwe Country Lead: Banking/MFI experience, RBZ relationships, manages licence partner relationship and local operations.

- Mobile Engineer: Flutter/React Native. Builds the app and integrations.

- Data/ML Engineer: Adapts scoring model. Can be remote (Ghana/Kenya — where the talent pool is deeper).

### Budget: $30K–$50K

Engineering setup, legal fees, licence partnership costs, initial team compensation.

## Phase 2: Closed Beta (Months 3–4)

Goal: 200–500 active users in Harare. Credit scoring model generating live predictions. First default data coming in.

### Lending Product (V1)

- Loan parameters: US$10–$50 initial loans, 30-day terms, 5% handling fee + interest.

- Target: 200–500 beta users recruited through WhatsApp groups, market trader associations, and direct outreach in Harare CBD, Mbare, and Chitungwiza.

- Scoring V1: Ghana model adapted with Zimbabwe mobile money data + psychometric assessment (Jippa Score questionnaire). Conservative initial limits.

- Disbursement via EcoCash wallet. Repayment via EcoCash + USSD + app.

### Data & Iteration

- Daily monitoring of repayment rates, default signals, and scoring model accuracy.

- A/B test scoring variables to identify which Zimbabwe-specific signals are most predictive.

- User feedback loops: in-app surveys, WhatsApp feedback channel, field interviews.

### Budget: $40K–$70K

Initial loan book ($20K–$40K in active loans at any time), ops costs, user acquisition.

## Phase 3: Open Beta (Months 5–6)

Goal: 1,000–3,000 active users. Loan limits increasing for repeat borrowers. USSD channel live. Scoring model refined with 2+ months of Zimbabwe data.

### Scale Lending

- Open registration to the public. Target Harare and Bulawayo.

- Increase loan limits for good borrowers: $50–$200 for 2nd loan, up to $500 for 3rd+ loan.

- Launch referral programme — refer-and-earn mechanics proven effective for app-based lending in African markets.

- Introduce credit score visibility: users see their Jippa Score and specific actions to improve it. This drives engagement and repayment behaviour (MTN Ghana’s YellowCredit showed 64% improvement in bill payments).

### Distribution

- Recruit 30–50 cash-in/cash-out agents in high-traffic locations (markets, bus termini, shopping centres). Budget $200–$500 per agent.

- WhatsApp-based marketing in market trader groups and informal sector communities.

- USSD channel (*XXX#) live for feature phone users.

### Savings Design (For Post-Pilot Launch)

- If operating under a deposit-taking partner: begin beta testing savings product with subset of users.

- Product: USD-denominated goal-based savings, group savings (stokvels/rounds), auto-save rules.

- Key insight: savings behaviour becomes a new scoring variable. Consistent savers get better loan terms. This is the flywheel.

### Budget: $50K–$100K

Growing loan book ($40K–$70K active), agent network, marketing, team.

## Phase 4: Validate & Raise (Months 7–8)

Goal: 5,000+ active borrowers. Default rate <5%. 3+ full loan cycles completed. Unit economics validated. Seed round conversations underway.

### Prove the Model

- Push toward 5,000 active users across Harare, Bulawayo, and satellite towns.

- Launch business loans for MSMEs (up to $2,000) — higher margin, larger ticket sizes.

- Compile performance data: default rates by cohort, scoring model accuracy (AUC), customer lifetime value, unit economics per loan.

### Fundraise

- Use pilot data to raise a seed round of $1M–$2M. Target: impact investors (FMO, BlueOrchard, Symbiotics — active funders of African digital lending), plus fintech-focused VCs (Accion Venture Lab, Quona Capital, Launch Africa).

- Seed capital funds: own licence acquisition ($50K–$150K for dormant MFI), savings and cards product launch, national scale-up, agent network expansion.

### Budget: $30K–$50K

Primarily fundraising costs, continued operations under existing capital.

# 3. Capital Plan

| Phase | Timeline | Budget | Key Milestone |
| --- | --- | --- | --- |
| Build | Months 1–2 | $30K–$50K | Licence partner signed, MVP built |
| Closed Beta | Months 3–4 | $40K–$70K | 200–500 users, first default data |
| Open Beta | Months 5–6 | $50K–$100K | 1,000–3,000 users, agents live |
| Validate | Months 7–8 | $30K–$50K | 5,000+ users, seed raise |
| TOTAL PILOT | 6–8 months | $100K–$250K | Model validated, ready to scale |

## Post-Pilot Capital (Seed Round)

| Use of Funds | Amount | Timeline |
| --- | --- | --- |
| Own MFI licence acquisition | $50K–$150K | Month 9–10 |
| Savings product launch | $100K–$200K | Month 9–12 |
| Virtual USD card launch | $150K–$300K | Month 11–14 |
| Loan book scale-up | $300K–$500K | Ongoing |
| Agent network + marketing | $200K–$300K | Ongoing |
| TOTAL SEED | $1M–$2M | Months 9–18 |

# 4. Key Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Currency volatility | Savings/loan values eroded. Borrowers may default during devaluation. | All products USD-denominated. ZiG exposure only where legally required. |
| Regulatory risk | RBZ has shut fintechs down (InnBucks 2022, Golix 2018). Compliance costs rising. | Partner with licensed MFI from day one. No grey-area operations. Proactive RBZ engagement. |
| Credit risk / defaults | Scoring model may underperform in Zimbabwe’s macro environment. | Start with $10–$50 loans. Progressive lending. 6+ months savings data before larger loans. Ghana model as baseline, recalibrated locally. |
| EcoCash dependency | 86% mobile money share. May restrict API access or charge high fees. | Multi-rail: EcoCash + InnBucks + Mukuru + bank transfers. Reduce single-point dependency. |
| InnBucks on Mambu | Completes digital bank transformation with competing products. | Speed. InnBucks migration is 12–18 months. Their DNA is QSR, not credit scoring. Our IP is 2–3 years ahead. |
| Licence partner risk | Partner’s compliance issues or disagreements could derail operations. | Thorough due diligence on partner. Contractual exit clauses. Parallel work on own licence application from month 4. |

# 5. Immediate Next Steps

- Legal Counsel: Engage a Zimbabwe-based corporate/banking lawyer. Budget $3K–$5K for initial engagement.

- Licence Partner Outreach: Approach 3–5 deposit-taking MFIs. Request RBZ’s current registered MFI list.

- Country Lead Search: Begin recruiting Zimbabwe-based ops lead. 5+ years banking/MFI, RBZ relationships.

- Data Source Mapping: Document all alternative data APIs in Zimbabwe: mobile money, utilities, KYC databases.

- Brand Setup: Reserve jippa.app domain, social handles. Register Jippa Technologies (Pvt) Ltd under COBE as a subsidiary of Base Technologies BV (Netherlands).

- Financial Model: Build 3-year model with loan book growth, unit economics, and breakeven analysis for fundraising.

This pilot is designed to run alongside other ventures. Phase 1 requires approximately 10–15 hours per week of founder time, primarily legal and planning. With the right Country Lead hired by month 2, the venture becomes largely operationally independent from Phase 2 onwards. The founder’s primary ongoing contributions are product vision, scoring model oversight, and fundraising.